## Project Plan Template
Project Deliverables
| PROJECT TITLE |  | START DATE
| Smart CBT |  | 2020-05-22 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
| Peter |  | 2020-08-10 |  |  | 81
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | Complete |  | 2020-05-22 | 2020-06-13 | 23 |  | Not Started
1.1 | System Requirement Gathering | Complete |  | 2020-05-22 | 2020-05-25 | 4 | Rquirement Gathered is available in an excel worksheet | In Progress
1.1.1 | Ui/ UX prototyping | Complete |  | 2020-05-25 | 2020-05-28 | 4 | UI/UX Design was translated into an actual Design | Complete
1.2 | Planning and system architecture | Complete |  | 2020-05-28 | 2020-05-30 | 3 | The Planning and System achitecture is represented in the database design | On Hold
1.3 | – Front End Design | Complete |  | 2020-05-30 | 2020-06-08 | 10 | TheComplete Source code is available on github and will be mail with this project
1.4 | – Front End Testing | Complete |  | 2020-06-08 | 2020-06-13 | 6 | The Test carried out on the Front End was successful both unit and Integration Test
NOTE : The Project sis 7 days behind Schedule next Delivery will be on